## Sheet1
i
i
i
i
i
i
Type | Tasks | Start Time | Finish Time | Duration
| Project Timeline | 2016-09-25 | 2016-12-05 | 71
Timeline | Sketch Timeline | 2016-09-25 | 2016-10-29 | 34
| Sketch Parts | 2016-09-25 | 2016-10-05 | 10
| Team Review | 2016-10-05 | 2016-10-10 | 5
Deadline | Submit sketches | 2016-10-28 | 2016-10-29 | 1
Timline | Part Timeline | 2016-10-10 | 2016-11-12 | 33
| Model Parts | 2016-10-10 | 2016-11-04 | 25
| Team Review | 2016-10-29 | 2016-11-03 | 5
Deadline | Submit part models | 2016-11-04 | 2016-11-05 | 1
| Drafts parts | 2016-11-02 | 2016-11-11 | 9
| Peer review #1 | 2016-11-02 | 2016-11-03 | 1
| Peer review #2 | 2016-11-05 | 2016-11-06 | 1
| Peer review #3 | 2016-11-09 | 2016-11-10 | 1
| Assemble/revise parts | 2016-11-04 | 2016-11-11 | 7
Deadline | Submit draft prints | 2016-11-11 | 2016-11-12 | 1
Timeline | Assembly Timeline | 2016-11-05 | 2016-11-19 | 14
| Prepare assembly | 2016-11-05 | 2016-11-14 | 9
| Generate Assem instr Views | 2016-11-09 | 2016-11-16 | 7
| Review assembly instructions | 2016-11-12 | 2016-11-17 | 5
Deadline | submit assembly instruc | 2016-11-18 | 2016-11-19 | 1
Timeline | Delivery Timeline | 2016-11-21 | 2016-12-05 | 14
| Prepare Presentation | 2016-11-21 | 2016-11-28 | 7
| Team Mock Presentation | 2016-11-28 | 2016-11-30 | 2
| Clean up of Project Files | 2016-11-30 | 2016-12-01 | 1
Deadline | present presentation | 2016-12-04 | 2016-12-05 | 1
Deadline | submit all project files | 2016-12-04 | 2016-12-05 | 1
Deadline | submit personal portfolios | 2016-12-04 | 2016-12-05 | 1
Formulas:
Start Time = MIN([Start Time, row below]:C77)
Finish Time = MAX([Finish Time, row below]:D52)