## Sheet2
Row Labels
assemble/revise parts**
Nov
drafts of parts
Nov
generate assem instr views
Nov
model parts
Oct
peer review parts, drafts #1
Nov
peer review parts, drafts #2
Nov
peer review parts, drafts #3
Nov
plan/prepare presentation
Nov
practice/revise presentation
Nov
prepare assembly instruc
Nov
present presentation
Dec
Project Timeline
Oct
r/r assembly instructions
Nov
sketch parts
Oct
Sketch Timeline
Oct
submit all project files
Dec
submit assembly instruc
Nov
submit draft prints
Nov
submit part models
Nov
submit personal portfolios
Dec
submit sketches
Oct
Grand Total

## Sheet1
i
i
i
i
i
i
Type | Tasks | Start Time | Finish Time | Duration
| Project Timeline | 2016-10-21 | 2016-12-05 | 45
Timeline | Sketch Timeline | 2016-10-21 | 2016-10-29 | 8
| Sketch Parts | 2016-10-21 | 2016-10-26 | 5
| Team Review | 2016-10-26 | 2016-10-28 | 2
Deadline | Submit sketches | 2016-10-28 | 2016-10-29 | 1
Timline | Part Timeline | 2016-10-28 | 2016-11-12 | 15
| Model Parts | 2016-10-28 | 2016-11-04 | 7
| Team Review | 2016-11-01 | 2016-11-03 | 2
Deadline | Submit part models | 2016-11-04 | 2016-11-05 | 1
| Drafts parts | 2016-11-02 | 2016-11-11 | 9
| Peer review #1 | 2016-11-02 | 2016-11-03 | 1
| Peer review #2 | 2016-11-05 | 2016-11-06 | 1
| Peer review #3 | 2016-11-09 | 2016-11-10 | 1
| Assemble/revise parts** | 2016-11-04 | 2016-11-11 | 7
Deadline | Submit draft prints | 2016-11-11 | 2016-11-12 | 1
Timeline | Assembly Timeline | 2016-11-05 | 2016-11-19 | 14
| Prepare assembly | 2016-11-05 | 2016-11-14 | 9
| Generate Assem instr Views | 2016-11-09 | 2016-11-16 | 7
| Review assembly instructions | 2016-11-12 | 2016-11-17 | 5
Deadline | submit assembly instruc | 2016-11-18 | 2016-11-19 | 1
Timeline | Delivery Timeline | 2016-11-21 | 2016-12-05 | 14
| Prepare Presentation | 2016-11-21 | 2016-11-28 | 7
| Team Mock Presentation | 2016-11-28 | 2016-11-30 | 2
| Clean up of Project Files | 2016-11-30 | 2016-12-01 | 1
Deadline | present presentation | 2016-12-04 | 2016-12-05 | 1
Deadline | submit all project files | 2016-12-04 | 2016-12-05 | 1
Deadline | submit personal portfolios | 2016-12-04 | 2016-12-05 | 1
Formulas:
Start Time = MIN([Start Time, row below]:C77)
Finish Time = MAX([Finish Time, row below]:D77)